## Sheet1
Name | Date | Clock In | Clock Out | Total Time | Work Done
Dean Reid Jr. | 2025-10-05 | 21:30 | 23:30 | 2 Hours | Designed Mockups for the Design Draft and Included them in the Report
Dean Reid Jr. | 2025-10-15 | 18:00 | 20:00 | 2 Hours | Researched Requirements/Constraints about Arduino VIN, Voltage Boosting/Stepdown, Sense vs Non-Sense Microcontroller Differences...
Dean Reid Jr. | 2025-10-16 | 11:00 | 12:00 | 1 Hour | Team Meeting to Select and Order Parts for Pre-Alpha Build
Dean Reid Jr. | 2025-10-18 | 17:00 | 18:00 | 1 Hour | Researched about how Foot Pressure is Measured and Distributed. Thinking of how to design Pressure Sensor Circuit to Measure Different Contact Zones
Dean Reid Jr. | 2025-10-19 | 21:30 | 23:30 | 2 Hours | Revised Mockups and Schematics for the Design Plan Revision
Dean Reid Jr. | 2025-10-24 | 22:00 | 2:00 | 4 Hours | Researched and Learning about MERN Stack Applications (Foundation of the Mobile App)
Dean Reid Jr. | 2025-10-25 | 17:00 | 18:00 | 1 Hour | Tested API Route Requests on POSTMAN
Dean Reid Jr. | 2025-10-25 | 20:00 | 21:00 | 1 Hour | Figured out how to get a bluetooth response from the Arduino, connect to the Mobile Device, and transfer data
Dean Reid Jr. | 2025-10-26 | 22:45 | 23:45 | 1 Hour | Collaborated with team members, ensuring assembly of the prototype
Dean Reid Jr. | 2025-10-31 | 2:00 | 6:00 | 4 Hours | Experimented with Account Based Data Storage based on JWT and MERN Stack
Dean Reid Jr. | 2025-11-06 | 3:00 | 5:00 | 2 Hours | Researched the differences between Bluetooth and BLE, how to setup a BLE peripheral device, and how to connect to BLE-compatible devices
Dean Reid Jr. | 2025-11-07 | 13:00 | 17:00 | 4 Hours | Created First Draft of BLE Code for the Arduino and Tested with nrfConnect BLE App
Dean Reid Jr. | 2025-11-07 | 20:00 | 22:00 | 2 Hours | Researched and Tackled Bug regarding Accelerometer Data Reading on Arduino Microcontroller
Dean Reid Jr. | 2025-11-08 | 16:00 | 18:00 | 2 Hours | Researched about the available BLE libraries for React Native and investigated the option of building a Swift-based app for IOS, since Expo requires Apple Development Account
Dean Reid Jr. | 2025-11-10 | 17:00 | 19:00 | 2 Hours | Documented Formatting of Structure of BLE Peripheral Service and Shared with Team. Additionally, testing sensor read delay timings to optimize for performance and usability with nrfConnect
Dean Reid Jr. | 2025-11-11 | 14:00 | 16:00 | 2 Hours | Team Meeting to Figure out the building and deployment process of App onto Android Interface
Dean Reid Jr. | 2025-11-13 | 14:00 | 17:00 | 3 Hours | Team Meeting to Build the Front-End App and Connect Arduino Data to the app (Building Debugging)
Dean Reid Jr. | 2025-11-13 | 18:00 | 19:00 | 1 Hour | Learned about TypeScript and Debugged Issue with BLE Front-End App Connection
Dean Reid Jr. | 2025-11-15 | 14:00 | 16:00 | 2 Hours | Figured out how to best compare data among the three force pressure sensors, what to calculate with the raw sensor data, and how to develop run tracking system that stores averages of tracked data
Dean Reid Jr. | 2025-11-16 | 15:00 | 18:00 | 3 Hours | Revised Arduino Code to Add Gyro Data, Account for Additional Force Pressure Sensors. Tested transmitted Gyroscope values and calibrated the microcontroller to ensure proper readings. Additional testing with nrfConnect
Dean Reid Jr. | 2025-11-16 | 20:00 | 23:00 | 3 Hours | Researched to design a system to check transmitted BLE values to ensure that they are as expected. Designed a method to handle errors during BLE data transfer and devised a method to handle unexpected disconnects from BLE communication